## Product Backlog
Virtual Bank Application for Kids — Product Backlog
Group SE-24 ¦ Module: Agile Software Development ¦ Date: 29 March 2026
ID | Epic | User Story | Acceptance Criteria | Priority (MoSCoW) | Story Points | Effort (hrs) | Status | Iteration | Assigned To | Notes | Dependencies
US-01 | Account Management | As a parent, I want to create a child bank account so that my child can start using the app. | Account created with name, age, PIN; saved to file; visible on dashboard. | Must | 5 | 8 | Planned | Iteration 1 | Group SE-24
US-02 | Account Management | As a child, I want to log in using my PIN so that I can access my account securely. | Correct PIN grants access; wrong PIN shows error; lockout after 3 fails. | Must | 3 | 5 | Planned | Iteration 1 | Group SE-24 |  | US-01
US-03 | Balance Tracking | As a child, I want to see my current balance so that I know how much money I have. | Balance displayed on home screen; updated after each transaction. | Must | 2 | 3 | Planned | Iteration 1 | Group SE-24 |  | US-01
US-04 | Deposit | As a parent, I want to deposit virtual money into my child's account so that they can receive earnings. | Parent enters amount; balance increases; transaction logged with date/time. | Must | 3 | 4 | Planned | Iteration 1 | Group SE-24 |  | US-01, US-03
US-05 | Withdrawal | As a child, I want to withdraw virtual money so that I can spend it on virtual items. | Child enters amount; sufficient balance check; balance decreases; logged. | Must | 3 | 4 | Planned | Iteration 1 | Group SE-24 |  | US-03
US-06 | Transaction History | As a child, I want to view my transaction history so that I can track my spending and earnings. | List shows date, type (deposit/withdrawal/reward), amount, balance after. | Must | 4 | 6 | Planned | Iteration 1 | Group SE-24 |  | US-04, US-05
US-07 | Task Management | As a parent, I want to create tasks with a reward amount so that my child can earn money by completing chores. | Task has title, description, reward; stored in file; visible to child. | Must | 5 | 8 | Planned | Iteration 2 | Group SE-24 |  | US-01
US-08 | Task Management | As a child, I want to see my pending tasks so that I know what I need to do to earn money. | Pending tasks listed; shows title, reward, due date. | Must | 3 | 4 | Planned | Iteration 2 | Group SE-24 |  | US-07
US-09 | Task Management | As a parent, I want to approve or reject completed tasks so that I control when rewards are paid. | Parent marks task done/rejected; if approved, balance is credited automatically. | Must | 4 | 6 | Planned | Iteration 2 | Group SE-24 |  | US-07, US-04
US-10 | Savings Goals | As a child, I want to set a savings goal so that I can save towards something I want. | Goal has name, target amount, optional deadline; progress bar shown. | Should | 4 | 6 | Planned | Iteration 2 | Group SE-24 |  | US-03
US-11 | Savings Goals | As a child, I want to transfer money to my savings goal so that I can track my progress. | Child selects goal, enters amount; deducted from current balance; goal progress updated. | Should | 3 | 4 | Planned | Iteration 2 | Group SE-24 |  | US-10, US-05
US-12 | Account Management | As a parent, I want to create both a current and a savings account for my child so that they learn account types. | Two account types available; each tracks balance separately. | Should | 4 | 6 | Planned | Iteration 2 | Group SE-24 |  | US-01
US-13 | Dashboard | As a child, I want a colourful, fun dashboard so that the app is engaging and easy to use. | Dashboard shows balance, recent transactions, active goals, pending tasks in child-friendly UI. | Should | 5 | 8 | Planned | Iteration 3 | Group SE-24 |  | US-03, US-06, US-08, US-10
US-14 | Notifications | As a child, I want an in-app notification when a task is approved so that I know I was paid. | Pop-up/banner appears after parent approves task; shows reward amount. | Could | 2 | 3 | Planned | Iteration 3 | Group SE-24 |  | US-09
US-15 | Savings Goals | As a child, I want to see a celebration animation when I reach a savings goal so that I feel rewarded. | When goal amount reached, a congratulations screen appears. | Could | 2 | 3 | Planned | Iteration 3 | Group SE-24 |  | US-11
US-16 | Reporting | As a parent, I want to export a simple monthly summary to a text file so that I can review my child's finances. | Parent presses 'Export'; .txt file generated with month's transactions and balance. | Could | 3 | 5 | Planned | Iteration 3 | Group SE-24 |  | US-06
US-17 | Security | As a parent, I want to set and change my child's PIN so that I maintain oversight. | Parent-only option to reset PIN; new PIN saved securely (hashed). | Could | 2 | 3 | Planned | Iteration 3 | Group SE-24 |  | US-02
Legend — MoSCoW Priority |  |  | Non-numeric input, negative amounts, empty fields all show descriptive error messages. | Must | 2 | 3 | Planned | Iteration 1 | Group SE-24 | Applies throughout
Must | Core — must be in first release
Should | Important — include if possible
Could | Nice to have — if time allows
Won't | Out of scope for this project

## Sprint Summary
Sprint / Iteration Summary
Iteration | Dates | Goal | Stories | Total Story Pts | Total Effort (hrs)
Iteration 1 | 1 Apr – 10 Apr 2026 | Core account, balance, deposit, withdrawal, transactions, error handling | US-01 to US-06, US-18 | 22 | 33
Iteration 2 | 13 Apr – 17 Apr 2026 | Task management, savings goals, dual account types | US-07 to US-12 | 23 | 36
Iteration 3 | 20 Apr – 24 Apr 2026 | Dashboard polish, notifications, export, security | US-13 to US-17 | 14 | 22